## Rate Card
Name | Jira Name | Monthly Salary
Alice |  | 80000
Bob |  | 60000
Charlie |  | 100000

## Holidays
Date | Description
2026-01-26 | Republic Day
2026-03-01 | Sample Holiday

## Resource List
Name | Jira Name | Date of Joining | Date of Separation | Period Start | Period End | Required Hours (Formula)
Alice |  | 2024-01-01 |  | 2026-01-01 | 2026-03-31 | 504
Bob |  | 2024-01-01 |  | 2026-01-01 | 2026-03-31 | 504
Charlie |  | 2024-01-01 |  | 2026-01-01 | 2026-03-31 | 504
Formulas:
Required Hours (Formula) = NETWORKDAYS.INTL([Period Start],[Period End],1, Holidays!A2:A100)*8

## Jira Dump
Author | Project | Issue | Epic | Original Estimate | Project Category | Started Day | Time Spent (hrs) | Project Key (formula) | Total Jira Hours (per author) | Required Hours (lookup) | Remark (To cap?) | Capped Hours (calc) | Monthly Salary (lookup) | Hourly Rate | Row Cost
Alice |  | SEYL-101 | FY26 Q4 |  | Implementation | 2026-01-05 | 90 | SEYL | 190 | 504 |  | 90 | 0 | 0 | 0
Alice |  | SEYL-102 | FY26 Q4 |  | Implementation | 2026-02-10 | 100 | SEYL | 190 | 504 |  | 100 | 0 | 0 | 0
Bob |  | ABCD-201 | FY26 Q4 |  | Consulting | 2026-01-15 | 120 | ABCD | 120 | 504 |  | 120 | 0 | 0 | 0
Charlie |  | SEYL-103 | FY26 Q4 |  | Implementation | 2026-03-05 | 150 | SEYL | 150 | 504 |  | 150 | 0 | 0 | 0

## Jira 2.0
SR Number | Customer Name | Product | Category | Category Code | Client Code | Sequence | Project Key (formula) | PO Amount | Revenue FY25 | Revenue FY26 | Total Signed HR Cost
1 | Seylan Bank | Lending | Implementation | IMP | SEYL | 1 | SEYL-IMP-01 | 500000 | 200000 | 100000 | 300000
2 | Alpha Corp | Payments | Consulting | CON | ABCD | 1 | ABCD-CON-01 | 300000 | 100000 | 50000 | 150000

## Overhead Pool
Quarter | HR Overhead Total | OPE Total | Infra Total | Commission Total
FY26 Q4 | 50000 | 25000 | 15000 | 10000

## Final Report
Project | Product | Category | Project Key | Project Status | PO Amount | Revenue FY25 | Revenue FY26 | Cumulative Revenue | Budget To Go | Total Signed HR Cost | Cost Till Last Quarter | Opening Remaining Signed HR Cost | Cost Incurred Current Quarter | Total Direct Cost Till Date | Closing Remaining Signed HR Cost | Allocated HR Overhead | OPE Cost | Infra Cost | Partnership Commission | Total Fully Loaded Cost | Gross Profit | Gross Margin %
Seylan Implementation | Lending | Implementation | SEYL-IMP-01 | Active | 500000 | 200000 | 100000 | 300000 | 200000 | 300000 | 150000 | 150000 | 0 | 150000 | 150000 | 34090.9091 | 17045.4545 | 10227.2727 | 6818.1818 | 218181.8182 | 81818.1818 | 0.27273
Alpha Consulting | Payments | Consulting | ABCD-CON-01 | Active | 300000 | 100000 | 50000 | 150000 | 150000 | 150000 | 70000 | 80000 | 0 | 70000 | 80000 | 15909.0909 | 7954.5455 | 4772.7273 | 3181.8182 | 101818.1818 | 48181.8182 | 0.32121